## Test Cases
ID | Module | Role | Steps | Expected Result | Status | Actual Result | Evidence | Defect ID | Tester | Date
LEAD-01 | Leads | Riya RM | Leads > Create Lead; fill every section incl. consent; click Create Lead | Lead opens in state NEW; mobile and email masked | Pass
LEAD-02 | Leads | Riya RM | Submit the create form empty | Required-field messages; no lead created | Pass | Requires Name and contact
LEAD-03 | Leads | Riya RM | Create a lead without consent details | Blocked; consent is mandatory | Pass | Consent is mandatory.
LEAD-04 | Leads | Riya RM | Create a second lead with the same mobile | Duplicate flag ('Dup:') appears on the list | Fail | Expected duplicate flag, got error (Raises Error)
LEAD-05 | Leads | Riya RM | On a NEW lead click Attempt Contact, then Mark In Progress | State NEW > CONTACT_ATTEMPTED > IN_PROGRESS; Contact Attempts shows 1 | Pass
LEAD-06 | Leads | Riya RM | Qualify Lead with applicant type and amount blank | Validation error; state unchanged | Fail | [Re-run required - invalid text System.Xml.XmlElement / blank income accepted]
LEAD-07 | Leads | Riya RM | Qualify with valid data, then Convert to Loan Application | QUALIFIED then CONVERTED; customer and application numbers shown; action buttons gone | Pass | (add requested amount dynamically)
LEAD-08 | Leads | Riya RM | On a converted lead try to qualify or disqualify | Not allowed (terminal state) | Pass
LEAD-09 | Leads | Riya RM | Disqualify a lead, then reopen it with a reason | DISQUALIFIED, then back to NEW; reopen needs a reason code | Fail | Once lead is disqualified, the status cannot be altered. (we should be able to reopen the case )
LEAD-10 | Leads | Riya RM | Filter the list by state, then Reset | List filters and resets; pagination still works | Pass
LEAD-11 | Leads | Two testers | Open the same lead in two tabs and change state in both | Second save rejected (version conflict), not silently overwritten | Not Run
CONS-01 | Consent | Riya RM | Open /customers/<id>/consents; Record New Consent, purpose SHARE_WITH_LENDER | Target field appears and is required; row shows ACTIVE | Pass
CONS-02 | Consent | Riya RM | Withdraw a consent | Status changes, button disappears, record stays | Pass
TASK-01 | Tasks | Riya RM | Create Task linked to a lead, with priority and SLA class | Task appears in Mine and All Visible | Fail | A record with the same unique value already exists.
TASK-02 | Tasks | Riya RM | Check the Mine tab after TASK-01 (code hard-codes owner 'usr_me', audit AUD-005) | Task appears under the logged-in user | Not Run
TASK-03 | Tasks | Riya RM | Complete a task with an outcome and note | Status Completed; gone from Open filter | Not Run
MSG-01 | Messaging | Asha Admin | New Template; Save & Approve Template | Row with APPROVED chip | Pass
MSG-02 | Messaging | Asha Admin | Template body using {{var}} not declared | Live preview and validation flag the variable | Fail | Templeate getting approved even without the declared variables ( Also the templates cannot e modified or even altered)
MSG-03 | Messaging | Asha Admin | Dispatch tab: pick lead, template, variables; Dispatch Message | In this build a red SEND_BLOCKED with reason code (no provider). Success is a defect | Fail | Expected a blocked send, got Message Successfully Sent!
MSG-04 | Messaging | Asha Admin | Dispatch outside 09:00-21:00, and for a customer with consent withdrawn | Blocked with the matching reason, never delivered | Fail | Messages are getting sent without
CMP-01 | Complaints | Riya RM | Record complaint with valid text | Acknowledgement reference shown | Fail | Complainant not found. (ref 01M5F0NSC6M59Q5NMRRS724RCH)
CMP-02 | Complaints | Riya RM | Enter under 10 characters, then text with a PAN-like or 12-digit number | Both rejected | Fail | [Re-run required - invalid text Recipient Masked:]
CMP-03 | Complaints | Asha Admin | Assign owner and due date; Start work; refer to lender; Resolve complaint | In progress, then Resolved; read-only until reopened | Not Run | [Re-run required - invalid text 9876****212]
CMP-04 | Complaints | Asha Admin | Reopen complaint with a reason | Resolution cleared; reason kept in audit | Not Run | [Re-run required - invalid text • Provider:]
LND-01 | Lenders | Asha Admin | New lender; add an empanelment and a contact | All three save and show on the lender page | Pass | (Check weather we need to uplaod any documents and if yes add option to do so. )
LND-02 | Lenders | Asha Admin | Change lender status to Paused or Terminated without a reason | Reason is required | Fail | [Re-run required - invalid text System.Xml.XmlElement / status change without reason]
LND-03 | Lenders | Asha Admin | Add a product, then New version with min amount above max | Rejected | Not Run
LND-04 | Lenders | Asha Admin | Add a second terms version | Old version kept; new version marked In force | Not Run
ADM-01 | Admin | Asha Admin | Create a branch, queue and team; add members to the queue | Saved; branch code cannot be changed afterwards | Not Run
ADM-02 | Admin | Asha Admin | Configuration: set routing mode, SLA, business hours; Save Configuration | 'Configuration successfully updated.'; values persist after refresh | Not Run
ADM-03 | Admin | Asha Admin | Set business hours end earlier than start | Should be rejected; if saved, log a defect | Not Run
USR-01 | Users | Asha Admin | Create a staff user with a role | User appears in directory; counts update | Not Run
USR-02 | Users | Asha Admin | Create a custom role with a few permissions | Shows as Custom Role; matrix reflects the choice | Not Run
RBAC-01 | Access | Sameer Sales | Sign in and scan the sidebar | No Administration group | Not Run
RBAC-02 | Access | Sameer Sales | Paste an admin URL such as /users or the configuration page | Access denied or redirect; API returns 403 in Network tab | Not Run
RBAC-03 | Access | Sameer Sales | Open a lead that belongs to another branch | Not found (404), not the lead's data | Not Run
AUTH-01 | Sign-in | Any | Sign in with a wrong password | Generic error; no hint which part was wrong | Not Run
AUTH-02 | Sign-in | Any | Sign in, enter a wrong then a correct 6-digit code | Wrong code rejected; correct code lands on Home | Not Run
AUTH-03 | Sign-in | Any | Security > Sign out other devices | Success message; other browser signed out | Not Run
AUTH-04 | Sign-in | Any | Let a session expire, then click a menu item | Redirected to sign-in, no blank page | Not Run
NTF-01 | Notifications | Any | Click the bell; switch All and Unread; Mark all read | Counts update | Not Run
NTF-02 | Notifications | Any | Gear icon > Notification Preferences (audit AUD-001) | Likely defect: dialog may fail to load. If it loads, change, Save Preferences, reopen and confirm persisted | Not Run
UI-01 | UI/UX | Any | Repeat the main flows at phone width (about 390 px) | No overflow; menus usable; dialogs fit | Not Run
UI-02 | UI/UX | Any | Use only the keyboard on the lead create form | Logical tab order; visible focus | Pass
AUTH-05 | Sign-in | Asha Admin | Open /mfa?enrol=true when an authenticator factor is already active | Enrolment mode activates; new QR code and secret displayed for enrolling additional authenticator | Not Run
DASH-01 | Access | Sameer Sales | Sign in as user with specific role (ROLE-SALES-EXEC, ROLE-LOAN-OPS, ROLE-FINANCE-EXEC) | Home route "/" resolves to dedicated role dashboard matching user role grants | Not Run
DASH-02 | Access | Asha Admin | Use role switcher dropdown on dashboard for multi-role user | Switching role updates dashboard context and action permissions seamlessly | Not Run
RBAC-04 | Access | Asha Admin | Audit Qloax tenant roles: verify action buttons displayed across screens match permission matrix exactly | Each role sees only authorized action buttons; unauthorized action buttons are hidden | Not Run
RBAC-05 | Access | Sameer Sales | Attempt newly guarded actions (commission.calculate, lender.manage, product.manage) | Zero-permission user blocked; old fallback role and new designated role allowed | Not Run
ELG-01 | Origination | Riya RM | Access Eligibility module (/eligibility or MOD-ELG) | Out of scope for this release | Out of Scope | Marked Out of Scope for this release per release requirements | Scope specification |  | Antigravity | 2026-10-22
CPT-01 | Connectors | Sameer Sales | Access Connector Portal (MOD-CPT) | Out of scope for this release | Out of Scope | Marked Out of Scope for this release per release requirements | Scope specification |  | Antigravity | 2026-10-22

## Legend
DSA-Agent Manual Test Plan - how to use
1. Run each case on the 'Test Cases' sheet as the role named in the Role column, using synthetic data only.
2. Fill the yellow columns: Status (dropdown), Actual Result, Evidence, Defect ID, Tester, Date.
3. On every Fail attach a screenshot, the exact error text and the Network-tab status code. Never paste tokens or real personal data.
4. Status values: Not Run, Pass, Fail, Blocked. The 'Summary' sheet counts them automatically.
5. Demo roles & accounts: Asha Admin (admin@alpha.com / ROLE-TENANT-ADMIN), Riya RM (rm1@alpha.com / ROLE-RM), Sameer Sales (sales1@alpha.com / ROLE-SALES-EXEC).
Source: cases derived from the DSA-Agent UI labels and the read-only audit; AUD-xxx IDs refer to that audit report.

## Summary
Status | Count | Share
Pass
Fail
Blocked
Not Run
Total
Cases by module | Cases | Failed
Leads
Consent
Tasks
Messaging
Complaints
Lenders
Admin
Users
Access
Sign-in
Notifications
UI/UX